PROPOSAL

IYRR-WQMA 2-YEAR WORK PLAN & BUDGET COMMITTEE REVIEW AND PSF PROPOSAL DEVELOPMENT WRITESHOP

Tentative Dates: July 27-29 2017

Venue: Somewhere in Cavite (preferred: IIRR, Silang Cavite)

BACKGROUND

Over the past two years, the IYRR-WQMA (Imus Ylang-Ylang Rivers Water Quality Management Area) Board has gone through a Strategic Planning process and adopted its first 10-year plan. Recently, it has started to finalized its first 2-year operations plan covering the period 2018-2019.

Most of the interventions identified in the 10-year and 2 year plans of the IYRR WQMA are inherently ecosystem-based because the results required for maintaining water quality relies on a protecting, rehabilitating and conserving a series ecosystems across the WQMA river basin. How this relates to climate change impacts and vulnerabilities of affected communities would be something that this writeshop should articulate?

Thus, this writeshop is being proposed among the members of the IYRR-WQMA board composed of several city/municipal LGUs, key Cavite provincial offices and other private stakeholders to identify these climate change adaptation and EbA-focused interventions proposed in the 10-year plan and effectively package them into a proposal following the standards of the PSF (Peoples Survival Fund) which the members of the WQMA board can then present to their respective SBs for endorsement so that it can proceed to a joint submission as a provincial-level PSF proposal; probably dived across thematic key proponents including the provincial government or key municipal/city LGUs and LCOs (local community organizations)

OBJECTIVES

At the end of this review and writeshop, the following should have been achieved:

- The IYRR-WQMA Committees have reviewed, updated and endorse for adoption by the WQMA Board, the proposed 2-Year Operations Work Plan and Budget

- Developed an outline for a IYRR-WQMA wide PSF Proposal based on relevant IYRR-WQMA targets within the next 10 years that are for climate change adaptation options; including those for EbA

- A schedule for next steps when the PSF proposal outline will be presented to the LCE and eventually to the respective LGU SBs for endorsement to qualify for a PSF proposal between August to October 2017

WRITESHOP DESIGN

| Schedule | Key Activities | Person in charge |
| --- | --- | --- |
| Day 1 AM 30 mins 1 hour 1 hour | Opening Committee Workshops to review the 2-year workplan Plenary Presentation and formal endorsement | Secretariat Committees Committees |
| Day 1 PM 30 mins 30 mins 2 hours 1 hour | Introductions Basic Concepts: CCA, EbA PSF Proposal Guidelines Writeshop Design Writeshop Session 1: Identifying CCA Options/ Interventions within the IYRR WQMA 10-year Plan (plenary group work) IYRR-WQMA 10 Year Plan Targets Assessment CCA Non- CCA EbA Non-EbA 1. Yes 2. Yes 3. 4. Writeshop Session 2: Assessing CC Vulnerabilities& Identifying Adaption Options of Systems of Interests within the IYRR-WMA and its 10-year targets (breakout session per LGU) LGU: _______________ Systems of Interests Climate Data Geo Hazards Potential Biophysical Impacts Potential Socio-Economic Impacts Adaptive Capacity of Vulnerable Communities Adaptation Options Related IYRR-WQMA Plans (CCA/Eba-focus) Plenary Presentation | Aksyon Kalikasan All (plenary) AK Facilitator Per LGU Per LGU |
| Schedule | Key Activities | Person in charge |
| Day 2 AM 1 hour 2 hours | Recap: Common Matrix from plenary presentation of day 1 Presentation: General Outline for a IYRR-WQMA PSF Proposal Writeshop Session 3: Drafting the Outline for a PSF Proposal (allow participants to choose which workshop groups to join) Project Details, Proponents, Project Background and Rationale (max of 4 slides) Project Goal/s and Objectives & Project Application Effectiveness (2 slides) Project Implementation (1 slide) Safeguards& Project Sustainability Plan (2 slides) Project Monitoring and Evaluation (1 slide) | AK All Participants |
| Day 2 PM 2 hours 3 hours | Plenary Presentation with Panel of Reactors (Critiquing) (Panels include: PGENRO, CCC, EMB, DA, Aksyon K) Further Editing of Workshop Group Presentation based on comments receive | Workshop Groups Workshop Groups |
| Day 3 AM 2 hours 1 hour | Final Presentation of Updated Proposal Components Next Steps Planning (Presenting to LCEs, SBs and securing endorsement) Closing | Workshop Groups Secretariat |

# Text boxes

Aksyon Kalikasan National Office

Rm. 10 Innovation and Community Empowerment Center (ICEC), International Institute for Rural Reconstruction (IIRR),

Aguinaldo Highway, Silang, Cavite

| Email: ecoactionsph@gmail.com | Mobile phone: 0915 2708776

Aksyon Kalikasan Ngayon! (Eco Actions Now!)